## Requirements
Area | Segment | Story | Comments | Estimation | Estimation assumptions | Release
Webpage | As a young vegetarian and farmer | I want to see the service description and learn how it works |  |  |  | MVP
Webpage | As a young vegetarian and farmer | I want to see the company description to know their idea and mission |  |  |  | MVP
Offer | As a local farmer | I want to add a YouTube link to my farm video |  |  |  | MVP
Offer | As a young vegetarian | I want to view farmers page and see short videos about ingredients supliers |  |  |  | MVP
Mailing | As a young vegetarian and farmer | I want to sign up to the newsletter to be notified about service changes |  |  |  | MVP
Analytics | As a site admin | I want to have all default user analytics to be sent to Google Analytics |  |  |  | MVP
Meals | As a site admin | I want to create 5 different recipe proposals for 1 and 2 weeks ahead |  |  |  | 1
Meals | As a site admin | I want to add pictures, a YouTube link and a description to every recipe |  |  |  | 1
Meals | As a young vegetarian | I want to view the menu for the upcoming week |  |  |  | 1
Meals | As a young vegetarian | I want to view the ingredients of a specific meal with nice meal pictures and a DIY video |  |  |  | 1
Order | As a young vegetarian | I want to choose a subscripion plan (number of meals per week to order) |  |  |  | 1
Order | As a young vegetarian | I want to pay for my order using one of the popular payment methods |  |  |  | 1
Order | As a young vegetarian | I want to receive an email with my order and payment summary |  |  |  | 1
Order | As a local farmer | I want to receive a monthly payment for my delivered products |  |  |  | 1
Order | As a site admin | I want to see all customer orders with their details, address details and payment status |  |  |  | 1
Order | As a site admin | I want to see all orders' payment status based on 3rd party payment platform integration |  |  |  | 1
User account | As a local farmer | I want to create an account to store my personal details for supply |  |  |  | 2
Offer | As a local farmer | I want to create my individual products page with pictures, descriptions and prices |  |  |  | 2
User account | As a young vegetarian | I want to create an account to store my personal details for order |  |  |  | 2
User account | As a young vegetarian | I want to login to my account to see my orders details |  |  |  | 2
Offer | As a young vegetarian | I want to view individual products offered by farmers |  |  |  | 2
Offer | As a young vegetarian | I want to order individual farmers' products |  |  |  | 2
Webpage | As a young vegetarian and farmer | I want to see an FAQ to find answers to my common questions |  |  |  | 2
Mobile support | As a site admin | I want the page to be responsive, to look nice on mobile devices |  |  |  | 3
Webpage | As a young vegetarian | I want to go to the blog page to view recent news |  |  |  | 3
Ratings | As a young vegetarian | I want to rate specific recipes to inform other customers about its quality |  |  |  | 3
Offer | As a local farmer | I want to set seasonal availablility of specific ingredients |  |  |  | 3
Mailing | As a site admin | I want to send a newsletter to all customers about new meal recipes available |  |  |  | 3

## Competitors & inspirations
https://marleyspoon.com/
https://www.hellofresh.com/
https://www.homechef.com/
https://www.makegoodfood.ca/en/home
https://dinnerly.com/
https://www.blueapron.com/
https://www.daily-harvest.com/
https://sunbasket.com/
https://justchopped.pl/
https://www.farmdrop.com/
https://www.oddbox.co.uk/
https://www.misfitsmarket.com/

## Important dates
Date | Comment
April | Some visuals to show on startup contest
May | Working solution for customers to allow them to make first orders based on fresh grown seasonal vegetables
July | Working panel for farmers to allow them to create video business cards and add custom products